## Slide 1: A Hybrid Remedy Implementation Case Study for Marsh Restoration in Brunswick Estuary, Georgia, USA
Presented by: Mark Reemts, PE, Anchor QEA
Collaborators: Ram Mohan, PE, PhD and Randy Brown, Anchor QEA Prashant Gupta and Richard Galloway, Honeywell International Inc. Tim Donegan, PE and Mike Marrone, Sevenson Environmental Services, Inc.

## Slide 2
Thin Layer Cover Application within the Brunswick Marsh

## Slide 3
How to effectively implement a remedy in sensitive marsh habitat while minimizing marsh impacts?

## Slide 4: 36,000 cy of dredging marsh creeks 18-inch removal across 11 acres TSCA and non-TSCA sediment
24,000 cy of sand backfill to restore creeks
12-inch cover
Thin Layer Cover over 11 acres of marsh
6-inch target placement
Restoration of disturbed areas
Clean fill placement and replanting of marsh access roads
Remedy Summary

## Slide 5: Site Layout
Offloading Area, Crew Dock
Trailers
and Parking
Sediment Processing Pad
TLC Slurry Equipment, Backfill Stockpiles
Support Areas
Dredging and Backfill
Thin Layer Cover
Pilot Study Area (Previously Completed)
Temporary Flow Control Structure
Temporary Flow Control Structure
Purvis
Creek
Domain 3
Creek
Eastern
Creek
LCP Ditch

## Slide 6: Floating Access – Dredging and Backfill
Standard floating platform with long reach excavator
Used for work in Purvis Creek and majority of side channels
Reconfigured for narrow access areas in creeks

## Slide 7: Temporary Flow Control Structure
Estuary experiences large tidal swings (7+ feet), fully dewatering the side channels
Temporary sheet pile structure retained water within the channels, allowing tidal exchange but increasing draft
Provided turbidity control during dredging operations

## Slide 8: Mat Access – Dredging, Backfill, and TLC
Temporary HDPE mat roadways constructed for access within the marsh
Crossings and extents limited where possible to reduce impact
Access roads restored following remedy implementation

## Slide 9: Thin Layer Cover Application
Full scale placement design was supported by data and observations from the pilot study
Sand material allowed ease of placement by rainbowing material
Real-time verification combined with thin lift application prevented overplacement

## Slide 10: Processing and Disposal
Sediment processing area separated into TSCA and non-TSCA footprints
Stabilized with Portland cement
Non-TSCA hauled by triaxle trucks
TSCA loaded to intermodal containers for rail shipment

## Slide 11: Verification
Dredging and backfill confirmed by pre-dredge, post-dredge, and post-backfill survey
  Single-beam for larger channel system with added topographic survey
  Transects and clustered topographic survey for smaller channels
Thin layer cover utilized grade stakes for QC verified by cores

## Slide 12: Lessons Learned – Survey
Survey required modifications during implementation
Topographic survey methods were necessary to capture elevation detail of certain areas
Full time survey allowed quick turnaround for verification and continued production

## Slide 13: Lessons Learned – Water Level Management
Temporary flow control structure significantly increased production capability of floating equipment
Reduced marsh impact by increasing floating access and reduced resuspension risk

## Slide 14: Lessons Learned – Thin Layer Cover
Material selection removed clogging risk
Custom nozzle provided good spray distance and spread
Application style matters—thinner lifts allowed more control, less impact to existing grasses

## Slide 15: Long-Term Monitoring
Initial program for years 1, 3, and 5 after construction completion
Sediment analytical, benthic community, vegetation reestablishment, water quality, fish tissue
First event completed December 2024, results pending

## Slide 16
Example Mat Access Road One Year Recovery, October 2024

## Slide 17
Figure 12: Mat access road recovery, Oct 2024
Example Thin Layer Cover One Year Recovery, October 2024

## Slide 18: Summary
Total 30,655 cy non-TSCA and 5,645 cy TSCA material removed
Lessons learned from pilot study and during implementation applied to improve construction and reduce marsh impact
Remedy completed on schedule, on budget
Initial marsh recovery progressing

## Slide 19
Mark Reemts, PE
Principal Engineer Anchor QEA
mreemts@anchorqea.com